# Workshop Agenda Planner

A fictional workshop about improving an internal request handoff. It uses 24 in-person participants at four tables of six, from 09:00 to 13:00 in local venue time. The 240 minutes include a break and all changeovers. This is a planning example, not a tested client outcome.

Use this editable example to assign real owners, rooms and outputs. Full block instructions and a CSV schedule accompany the online template.

# Objectives

Compare options for a clearer request handoff.

Design a small test whose completion and observations can be checked.

# Outputs

An option sheet per table, separating facts, assumptions, criteria and unresolved questions.

One consolidated small-test plan, including an accepted owner, due date, review date and evidence to check.

# Before the day

Confirm a facilitator, a sponsor with stated decision authority and one recorder at each of four tables. The 24 participants include the table recorders; facilitator and sponsor are additional roles unless assigned from the group.

Prepare a short fictional or approved, redacted request-handoff example. Remove customer identifiers and separate confirmed observations from assumptions.

Provide paper, pens, option-sheet and test-plan headings, a visible timer and a shared board. Agree a private place for approved notes.

Check accessible routes, seating, print size and hearing needs in advance. Offer individual writing and a recorder as alternatives to speaking. No one must disclose personal experience.

Ask the sponsor to state the decision boundary, available time and resources. If essential evidence or authority is missing, use the session to document questions instead of forcing a decision.

# When to adapt this plan

This example covers one bounded process question. It does not establish that the chosen change will improve results.

Use a different process for confidential personnel disputes, acute conflict, or high-stakes decisions without the required expertise and authority.

Remote and hybrid sessions need a redesigned interaction, access and timing plan. This example assumes everyone is in the room.

Do not scale beyond 24 participants without reviewing staffing, table reporting time and access. Protect the break and final ownership review; reduce scope if time slips.

# First half

Local venue time. Durations include the stated changeovers. Replace role names with assigned people before the day.

| Time | Session and location | Output and changeover |
| --- | --- | --- |
| 09:00-09:15 15 min | Set the contract Main room ¦ Whole group Owner: Facilitator | Option sheet: question, boundaries and decision criteria Changeover: Included in the final recording minutes; no extra time. |
| 09:15-09:45 30 min | Read the evidence Main room ¦ Four tables of six Owner: Facilitator | Option sheet: facts, assumptions and missing evidence Changeover: Included in the final recording minutes; no extra time. |
| 09:45-10:25 40 min | Generate options Main room ¦ Four tables of six Owner: Facilitator and table recorders | Option sheet: distinct approaches and open questions Changeover: Included in the final recording minutes; no extra time. |
| 10:25-10:40 15 min | Break Main room ¦ Whole group Owner: Facilitator | No work expected Changeover: Return by 10:40; movement is included in the break. |
| 10:40-11:10 30 min | Compare options Main room ¦ Whole group Owner: Facilitator | Option sheet: comparisons against agreed criteria Changeover: Included in the final recording minutes; no extra time. |

# Second half

Local venue time. Durations include the stated changeovers. Replace role names with assigned people before the day.

| Time | Session and location | Output and changeover |
| --- | --- | --- |
| 11:10-11:30 20 min | Choose a test Main room ¦ Whole group Owner: Sponsor decision owner | Small-test plan: selected question and recorded objections Changeover: Included in the final recording minutes; no extra time. |
| 11:30-12:10 40 min | Build the test plan Main room ¦ Four tables of six Owner: Facilitator and table recorders | Small-test plan: steps, starting process and observations to collect Changeover: Included in the final recording minutes; no extra time. |
| 12:10-12:35 25 min | Challenge the plan Main room ¦ Whole group Owner: Facilitator | Small-test plan: revised risks and stop conditions Changeover: Included in the final recording minutes; no extra time. |
| 12:35-12:55 20 min | Accept ownership Main room ¦ Whole group Owner: Sponsor decision owner | Small-test plan: accepted owner, dates and evidence access Changeover: Included in the final recording minutes; no extra time. |
| 12:55-13:00 5 min | Close Main room ¦ Whole group Owner: Facilitator | Small-test plan: agreed next step and sharing boundary Changeover: Included in the final recording minutes; no extra time. |

# Instructions for each block

## 09:00 Set the contract

Spend 3 minutes framing the handoff question, 4 clarifying authority and constraints, and 6 agreeing criteria such as clarity, effort and access. Use the last 2 minutes to record the contract and move to the evidence.

## 09:15 Read the evidence

Spend 5 minutes reading the approved example, 10 marking facts separately from assumptions, and 12 discussing missing evidence at each table. Record open questions and reset the board in the final 3 minutes. Do not copy private identifiers.

## 09:45 Generate options

Use 5 minutes to frame the question. Give 5 minutes for quiet individual ideas, 10 to share or pass, and 15 to develop distinct options. Each table records its options and prepares one short explanation in the final 5 minutes.

## 10:25 Break

Take the full 15 minutes away from the task. Offer a quiet resting place. Return by 10:40; any walking time is inside this break.

## 10:40 Compare options

Use 2 minutes to restate the agreed criteria. Give each of four tables 3 minutes to explain its options, for 12 minutes total. Spend 13 comparing tradeoffs and missing evidence. Use the last 3 minutes to record the comparison.

## 11:10 Choose a test

Spend 5 minutes reviewing constraints, 8 examining objections and 5 on the sponsor decision. The sponsor selects a bounded test only within the agreed authority. Record the reason and unresolved objections in the final 2 minutes. If evidence or authority is insufficient, record the gap instead.

## 11:30 Build the test plan

Use 5 minutes to assign four parts of one plan: steps, starting process and observations, risks and stop conditions, and resources and access. Tables work in parallel for 15 minutes. Spend 15 combining their parts into one plan and 5 recording remaining questions.

## 12:10 Challenge the plan

Use 5 minutes to read the combined plan, 8 to identify failure cases, and 10 to revise its steps and stop conditions. Record changes and remaining uncertainty in the final 2 minutes. A plausible plan is not evidence that the test has worked.

## 12:35 Accept ownership

Spend 5 minutes proposing the action owner and evidence reviewer, 8 agreeing due and review dates plus evidence access, and 5 obtaining explicit acceptance. Record open assignments in the final 2 minutes. Do not assign work to absent colleagues. Keep unresolved ownership visible.

## 12:55 Close

Use 2 minutes to restate the agreed plan, 2 to confirm sharing permissions and the next review, and 1 to save the approved record and close. Invite written feedback or a pass; no public promise or group photo is required.

# Illustrative redesign notes

These comparisons describe a fictional agenda, not measured results from a delivered workshop.

Before: A fictional four-hour workshop jumps from problem talk to a preferred solution.

After: Read evidence, generate options, agree criteria and record the sponsor decision before planning a test.

Reason: This makes assumptions, tradeoffs and decision authority inspectable. It does not guarantee the best choice.

Before: A fictional agenda uses its final minutes for more discussion and leaves ownership unspecified.

After: Reserve 20 minutes for accepted ownership and evidence, followed by a five-minute close.

Reason: A written plan allows a later review. Whether anyone completes it must still be observed.

# Follow up

Share only the approved option sheets and test plan with the agreed group. Keep private evidence in the approved location.

At the agreed review date, record what happened and what remains unknown. No reply is not proof that no work occurred.

Compare the observations with the recorded starting process. Decide whether to continue, revise or stop; a completed action alone does not establish impact.

# Your action record

Action: __________________________________________

Owner: __________________________________________

Date: __________________________________________

Evidence to check: __________________________________________

Review date: __________________________________________

Sharing permission: __________________________________________

Source and full instructions: https://unitedwetransform.com/workshop-agenda-template/